## Sheet1
For The Win Feature List
Phase | Area | Sub Feature | Detail | 2024-01-05 | 2024-01-12 | 2024-01-19 | 2024-01-26 | 2024-02-02 | 2024-02-09 | 2024-02-16 | 2024-02-23
Pre playtest | Club | stadium | effect on match | 2024-01-26: Holiday | need to refine values and their effect
| Club | stadium | upgrade system | [8 empty] | working from turnfile, front end to populate turnfile | bar: 2024-01-05
| Players |  | potential | [8 empty] | check adding to right players | bar: 2024-01-05
| Club | staff | training | [8 empty] | working from turnfile, front end to populate turnfile | bar: 2024-01-05
| Club | staff | upgrade system | [8 empty] | working from turnfile, front end to populate turnfile | bar: 2024-01-05
| Admin |  | player turnsheet | [8 empty] | initial form for working elements, team selection, training, upgrades. JS validation | bar: 2024-01-05
| Admin |  | users | bar: 2024-01-12
| Match |  | commentary | [8 empty] | need to enhance comments | bar: 2024-01-12
| Players |  | Positions | [8 empty] | introduce L and R players and maybe D and A for mids as tactics can influence these players skills/perf calc | bar: 2024-01-19
| Match |  | tactics | bar: 2024-01-19
| Match |  | aggression | bar: 2024-02-02
| Players |  | fitness | bar: 2024-02-09
| Players |  | star stat | [8 empty] | one per player, vairied affect | bar: 2024-02-16
| Players |  | value and contract | [8 empty] | weekly contract so it decreases each week | bar: 2024-02-16
| Players |  | blend | [8 empty] | blend value, average team area, higher = bad | bar: 2024-02-23
| Players |  | rework seed files | bar: 2024-02-23
| Admin |  | deployment | bar: 2024-02-23
Post playtest | Club |  | special events like community chance in monopoly
| Transfers |  | list a player
| Transfers |  | loan
| Transfers |  | sell / buy a player
| Finance |  | sponsorship
| Finance |  | ticket price
| Match |  | attendance
| Club |  | club facilities
| Finance |  | basic structure including weekly costs
| Match |  | cards
| Match |  | substitutions
| Club |  | board interactions
| Fixtures |  | edit
| Fixtures |  | cup comps
Pre launch | admin |  | club creation
| admin |  | payment system
| admin |  | player emails/comms
| General |  | international management
| General |  | manager rating
| Players |  | generate youth player